## Action Items
ID | Title | Description | Category | Owner | Source | Priority | Status | Last Updated
002 | Add carrier charges and carrier name fields to ticket | Document requirements in the existing ticket for new custom fields to store carrier charges and carrier name from the shipping integration, ensuring values flow through to invoices and reports. | Freight Revenue | Satbere | 2026-04-14 | High | Complete | 2026-04-14
003 | Add markup parameter and security controls to ticket | Add requirements to the existing ticket for a default markup percentage parameter (per legal entity) and manager-only edit rights for markup and total charges fields in both the shipping rate window and Maintain Charges. | Security & Access | Satbere | 2026-04-14 | High | Complete | 2026-04-14
004 | Review technical approach with developer | Satbere to walk through technical impact with the developer — tables affected, required privileges, and data flow from shipping integration to sales order and invoice — and report back with feasibility and effort estimate. | Development Review | Satbere | 2026-04-14 | High | Complete | 2026-04-20
001 | Export global delivery terms list from Dynamics | Export the complete global delivery terms list with descriptions from Dynamics and share for review. Needed to standardize terms, remove unused ones, and align with actual shipment usage across legal entities. | Delivery Terms | Satbere | 2026-04-14 | Medium | Complete | 2026-04-14
006 | Meet with divisional leaders on delivery terms cleanup | Alan to meet with divisional leaders to discuss which delivery terms to keep or remove, then finalize the cleanup list in Dynamics based on the exported terms and actual usage data (e.g. Collect ~7,000 shipments vs. CIF only 1). | Delivery Terms | Alan | 2026-04-14 | Medium | Complete | 2026-04-20
005 | Confirm priority order of changes within ticket | Agree on the sequence of development work within the existing ticket — markup parameterization, security controls, and carrier charges fields — before handing off to the developer to start. | Ticketing & Support | Alan | 2026-04-14 | Medium | Open | 2026-04-14
008 | Create and deploy an "Other" shipping charge code for cases when shipping... | Create and deploy an "Other" shipping charge code for cases when shipping integration is disabled. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
009 | Issue updated work instructions requiring charge code selection at shipment... | Issue updated work instructions requiring charge code selection at shipment when disabling shipping integration. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
010 | Enforce selection of the "Other" charge code as a temporary control while... | Enforce selection of the "Other" charge code as a temporary control while customization is scoped. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
011 | Scope and assign ownership for the long-term customization to make the... | Scope and assign ownership for the long-term customization to make the charge code mandatory and auto-populate when integration is disabled (involve Cambay and Paul). | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
012 | Schedule and conduct a cross-functional session to map freight process... | Schedule and conduct a cross-functional session to map freight process fields end-to-end (inside sales, warehouse, SMEs: Paul, Amy, possibly Donna). | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
013 | Prepare a physical inventory follow-up package: root cause analysis,... | Prepare a physical inventory follow-up package: root cause analysis, training plans, "ZZ" cleanup status, cycle count plan, and system changes. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
014 | Validate Port Arthur and La Porte incidents against the mid-April ticket... | Validate Port Arthur and La Porte incidents against the mid-April ticket resolution; report findings and confirm timing (pre- or post-resolution). | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
015 | Keep Justin cc'd on cycle count and freight-related coordination emails to... | Keep Justin cc'd on cycle count and freight-related coordination emails to maintain traction. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
016 | Confirm next week's meeting date (Thursday) details and agenda. | Confirm next week's meeting date (Thursday) details and agenda. | Freight Operations | TBD | 05-18 Weekly Meeting: Freight Capture Fixes, Process Mapping, and Inventory Controls | Medium | Open | 2026-05-18
017 | Determine whether, for multi-person approval levels, notifications should be... | Determine whether, for multi-person approval levels, notifications should be sent to all individuals and whether approval is required from one person or all. -- Alan | Inventory Management | Alan | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
018 | Confirm with Corey and other stakeholders that the approval trigger should... | Confirm with Corey and other stakeholders that the approval trigger should be the "net journal" value, not "net monthly." -- Alan | Inventory Management | Alan | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
019 | Clarify whether an adjustment exceeding a certain threshold (e.g., Level 3)... | Clarify whether an adjustment exceeding a certain threshold (e.g., Level 3) should route directly to that level, or if it must first pass through lower approval levels (Level 1 and 2). Raise this on the weekly call with VPs and divisional leaders. -- Alan | Inventory Management | Alan | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
020 | Add Justin, Corey, Dawn Hector, Rocky, and Will to the discussion to gather... | Add Justin, Corey, Dawn Hector, Rocky, and Will to the discussion to gather input on the proposed workflow questions. -- Alan | Inventory Management | Alan | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
021 | Internally discuss with Paul whether to use role-based assignments or user... | Internally discuss with Paul whether to use role-based assignments or user groups for managing approvers in the workflow, given inconsistent job titles across sites. -- Amy | Inventory Management | Amy | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
022 | Configure email notifications for approvals to include a direct link to the... | Configure email notifications for approvals to include a direct link to the journal in D365 and a calculated field showing the net journal value. -- Donovan | Inventory Management | Donovan | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
023 | Schedule a follow-up meeting for the week of May 18, 2026, after internal... | Schedule a follow-up meeting for the week of May 18, 2026, after internal questions are answered. Confirm the final date and time by May 15, 2026. -- Amy | Inventory Management | Amy | 05-13 Weekly Meeting: Inventory Adjustment Workflow Design | Medium | Open | 2026-05-18
024 | Add a new API-mapped field to capture UPS discounted/carrier rate; review... | Add a new API-mapped field to capture UPS discounted/carrier rate; review UPS docs and contact UPS to identify exact field. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
025 | Configure carrier-level markups for computing published rate (where needed)... | Configure carrier-level markups for computing published rate (where needed) and customer charge; remove per-transaction markup UI elements and the integration page "markup" column. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
026 | Save and display Carrier Rate, Published Rate, and Customer Charge on order... | Save and display Carrier Rate, Published Rate, and Customer Charge on order tracking; ensure Customer Charge flows to Sales Order Maintain Charges and invoices; make integration-populated fields non-editable. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
027 | Implement manual "Disable shipping integration" parameter per carrier... | Implement manual "Disable shipping integration" parameter per carrier (default false); enforce UI behavior (API-populated vs manual entry). | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
028 | Add packing slip posting validation to require a shipping integration... | Add packing slip posting validation to require a shipping integration record, with a global "Require shipping integration" toggle; define handling/exemptions for direct deliveries. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
029 | For disabled integration: enforce manual entry of carrier rate only; system... | For disabled integration: enforce manual entry of carrier rate only; system applies markups automatically; prohibit manual markups. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
030 | Validate in UAT the invoice charge application issue (Incident 136430);... | Validate in UAT the invoice charge application issue (Incident 136430); confirm if empty shipping carrier causes failure; make shipping carrier mandatory and link carriers to charge codes. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
031 | Define precise field names for BI; plan schema/report updates to incorporate... | Define precise field names for BI; plan schema/report updates to incorporate new fields without losing historical interpretability. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
032 | Verify development approach to avoid per-carrier fragmentation; ensure FedEx... | Verify development approach to avoid per-carrier fragmentation; ensure FedEx integration adopts the standardized logic. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
033 | Contact UPS/account manager to clarify label tag impacts; determine go/no-go... | Contact UPS/account manager to clarify label tag impacts; determine go/no-go for mapping both "Shipper" and "Ship From" to warehouse. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
034 | Clarify currency sourcing/mapping on the shipping integration form; document... | Clarify currency sourcing/mapping on the shipping integration form; document multi-region handling and any per-carrier overrides. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
035 | Decide policy on storing/displaying published rates for Collect/Third Party... | Decide policy on storing/displaying published rates for Collect/Third Party scenarios; ensure customer charge remains zero and carrier rate is zeroed post-approval. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
036 | Define data model for customer carrier account numbers (customer vs delivery... | Define data model for customer carrier account numbers (customer vs delivery address with per-carrier detail); assign ownership and ADO tracking. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
037 | Coordinate with AR to redesign invoice output separating freight from... | Coordinate with AR to redesign invoice output separating freight from miscellaneous; assign owner and timeline. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
038 | Standardize an initial carrier list (UPS, FedEx, DHL, WWEX, "Other/Hot... | Standardize an initial carrier list (UPS, FedEx, DHL, WWEX, "Other/Hot Shot," plus key locals) and communicate to users. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
039 | Consolidate tickets; update the FDD and strike through deprecated items;... | Consolidate tickets; update the FDD and strike through deprecated items; deliver change diff and documentation for review by 2026-05-15. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
040 | Schedule cycle counts/ABC session for the week of 2026-05-18 and confirm... | Schedule cycle counts/ABC session for the week of 2026-05-18 and confirm attendees. | Shipping Integration | TBD | 05-12 Meeting: Standardizing Carrier Rate Fields, Markups, and Shipping Integration Controls | Medium | Open | 2026-05-18
041 | Alan to share details on ticket 21281 with Steve via email. | Alan to share details on ticket 21281 with Steve via email. | Freight Policy | TBD | 05-12 Weekly Meeting: Freight Policy System Requirements and Ticket Prioritization | Medium | Open | 2026-05-18
042 | Justin to obtain a new ticket number for the P1 item (restricting delivery... | Justin to obtain a new ticket number for the P1 item (restricting delivery options). | Freight Policy | TBD | 05-12 Weekly Meeting: Freight Policy System Requirements and Ticket Prioritization | Medium | Open | 2026-05-18
043 | Scott to connect Justin with Cliff to access P21 data for the manual update... | Scott to connect Justin with Cliff to access P21 data for the manual update process. | Freight Policy | TBD | 05-12 Weekly Meeting: Freight Policy System Requirements and Ticket Prioritization | Medium | Open | 2026-05-18
044 | Speaker 2 to email reconciled "final draft" and "final copy" communication... | Speaker 2 to email reconciled "final draft" and "final copy" communication materials to the team. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
045 | Don to reconcile his version with Speaker 2's and send/plug changes. | Don to reconcile his version with Speaker 2's and send/plug changes. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
046 | Alan to create a 1-2 page guide with screenshots on entering collect account... | Alan to create a 1-2 page guide with screenshots on entering collect account numbers so they print on pick tickets. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
047 | Alan to support warehouse/branch training on correct fields, maintain... | Alan to support warehouse/branch training on correct fields, maintain charges, and shipping integration; define escalation contacts and own support via existing calls. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
048 | Include intercompany freight scenarios in field mapping; address manual... | Include intercompany freight scenarios in field mapping; address manual linkage of charges to branch/customer orders; define an interim SOP to prevent double/triple billing. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
049 | Conduct time studies for Rocky's team this week and plan AT baseline by end... | Conduct time studies for Rocky's team this week and plan AT baseline by end of month; include direct ship, VAC production/service orders, and BOA approval delay measurements. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
050 | Compile and share data on top-line customers not paying freight and total... | Compile and share data on top-line customers not paying freight and total freight paid on their behalf before the upcoming call; begin outreach to flip them to paying freight. | Freight Policy | TBD | 05-11 Team Meeting: Freight Policy Communication, D365 Collect Process, Intercompany Freight, and Time Study Efficiency | Medium | Open | 2026-05-18
051 | May 12, 2026: Cliff's team will meet with an SA Global expert to explore... | May 12, 2026: Cliff's team will meet with an SA Global expert to explore Dynamics 365's full capabilities for customer data. | ERP/D365 | TBD | 05-11 Meeting: ERP Conversion Data Issues & Dynamics 365 Workflow | Medium | Open | 2026-05-18
052 | Use insights from this meeting to inform the discussion with the Dynamics... | Use insights from this meeting to inform the discussion with the Dynamics expert. | ERP/D365 | TBD | 05-11 Meeting: ERP Conversion Data Issues & Dynamics 365 Workflow | Medium | Open | 2026-05-18
053 | Cliff may contact the Set Point team with follow-up questions. | Cliff may contact the Set Point team with follow-up questions. | ERP/D365 | TBD | 05-11 Meeting: ERP Conversion Data Issues & Dynamics 365 Workflow | Medium | Open | 2026-05-18
054 | Christoph to set up proactive monthly sessions with Purchasing, Projects,... | Christoph to set up proactive monthly sessions with Purchasing, Projects, and Order Desk teams in Europe. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
055 | Christoph to talk to Rick about the narrator's future plans and potential... | Christoph to talk to Rick about the narrator's future plans and potential team staffing. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
056 | Schedule calls with various departments for the week of May 11, 2026, to... | Schedule calls with various departments for the week of May 11, 2026, to gain more insight into the inbound freight process. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
057 | Connect with Daraj after the current call to align on the outbound freight... | Connect with Daraj after the current call to align on the outbound freight details. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
058 | Schedule a meeting with the Canbay team to discuss and begin development of... | Schedule a meeting with the Canbay team to discuss and begin development of system configurations. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
059 | Spend Monday, May 11, 2026, with the project order handler in the warehouse... | Spend Monday, May 11, 2026, with the project order handler in the warehouse to understand why packing and containerizing orders is taking so long. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
060 | Schedule a cycle count for the week of May 11, 2026 (will be early morning... | Schedule a cycle count for the week of May 11, 2026 (will be early morning for the Las Vegas participant). | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
061 | Investigate the root cause of the "no put location" issue (Ticket 136469) by... | Investigate the root cause of the "no put location" issue (Ticket 136469) by checking location directives; ask Amy to assign if necessary. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
062 | Provide the ticket number and a sales order example for the "no put... | Provide the ticket number and a sales order example for the "no put location" issue. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
063 | Look into two specific RMAs that need attention. | Look into two specific RMAs that need attention. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
064 | Alan needs to follow up with Justin about the status of Vidal. | Alan needs to follow up with Justin about the status of Vidal. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
065 | US team to roll out the new three-tier delivery terms. | US team to roll out the new three-tier delivery terms. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
066 | The discrepancy between US and European delivery terms needs to be addressed. | The discrepancy between US and European delivery terms needs to be addressed. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
067 | Help Cliff with translating P21 fields into the new system. | Help Cliff with translating P21 fields into the new system. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
068 | The speaker needs to contact Justin regarding their role and potential... | The speaker needs to contact Justin regarding their role and potential organizational changes. | ERP/D365 | TBD | 05-08 Reasoning Note: Team Dynamics, European Branch Issues, and System Updates | Medium | Open | 2026-05-18
069 | Compile a written SOP mapping intended vs. actual freight processes for... | Compile a written SOP mapping intended vs. actual freight processes for Setpoint (inbound and outbound), then extend to WO and AT. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
070 | Review a Dynamics sales order screen to list shipping-related fields... | Review a Dynamics sales order screen to list shipping-related fields (carrier, mode, method) and dropdown values; document auto-default behavior and warehouse field usage on pick lists/waves. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
071 | Validate who applies significant inbound freight charges to sales orders... | Validate who applies significant inbound freight charges to sales orders across Setpoint, AT, and WO; define owners, steps, and traceability from supplier invoice to customer charge. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
072 | Investigate and fix the bug allowing charges without charge codes when... | Investigate and fix the bug allowing charges without charge codes when integration is disabled; add to open items with Cambe. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
073 | Review and enforce delivery term requirements on sales order headers to... | Review and enforce delivery term requirements on sales order headers to ensure freight flows to invoices and reports. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
074 | Confirm the three example orders from the chat and reconcile discrepancies... | Confirm the three example orders from the chat and reconcile discrepancies in Power BI freight recovery report; verify alignment across source reports and all charge scenarios. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
075 | Draft a clean, standard outbound shipping process flow; add documented... | Draft a clean, standard outbound shipping process flow; add documented exception paths for method changes with approval and audit steps. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
076 | Engage business stakeholders to rationalize modes of delivery and define... | Engage business stakeholders to rationalize modes of delivery and define delivery terms; update the open SR with inputs. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
077 | Provide warehouse with clear instructions for "air freight" selections... | Provide warehouse with clear instructions for "air freight" selections (contacts, service types, who to call). | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
078 | Align on whether to process shipments via integration or outside it and... | Align on whether to process shipments via integration or outside it and document charge capture steps and decision rules. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
079 | Review each shipping carrier and list available carrier services; assess... | Review each shipping carrier and list available carrier services; assess which to retain and standardize. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
080 | Define and standardize the method for capturing freight (Maintain charges... | Define and standardize the method for capturing freight (Maintain charges vs. Item ID) and invoice itemization requirements; include governance for customer-specific needs. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
081 | Map and document exceptions for non-integrated shipments; propose actions to... | Map and document exceptions for non-integrated shipments; propose actions to reduce or eliminate these paths and incorporate markup percentage logic; include Justin. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
082 | Collect and analyze specific outbound examples with missing amounts in... | Collect and analyze specific outbound examples with missing amounts in Maintain charges; identify root causes and user process errors. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
083 | Coordinate with Supply Chain to resume WWEX hot shot negotiations and... | Coordinate with Supply Chain to resume WWEX hot shot negotiations and integration readiness; reconnect with Nathan Brunell on WWEX/hot shot consolidation. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
084 | Engage Europe operations to plan separate outbound freight standardization. | Engage Europe operations to plan separate outbound freight standardization. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
085 | Schedule focused sessions with Alan, Daraj, and team to walk through... | Schedule focused sessions with Alan, Daraj, and team to walk through shipment integration steps and data flow. | Freight Operations | TBD | 05-07 Meeting: Freight Capture, Shipping Integration, and Invoice Governance in Dynamics 365 | Medium | Open | 2026-05-18
086 | will document the proposed changes for the shipping integration screen and... | [Speaker 1] will document the proposed changes for the shipping integration screen and share them with Sabir. | Shipping Integration | Speaker 1 | 05-01 Meeting: Shipping Integration Enhancements & Standardization | Medium | Open | 2026-05-18
087 | will follow up with Sabir to schedule a meeting to review the proposed changes. | [Speaker 1] will follow up with Sabir to schedule a meeting to review the proposed changes. | Shipping Integration | Speaker 1 | 05-01 Meeting: Shipping Integration Enhancements & Standardization | Medium | Open | 2026-05-18
088 | will email SunSource to confirm the correct markup percentage (20% vs. 25%)... | [Speaker 3] will email SunSource to confirm the correct markup percentage (20% vs. 25%) to ensure alignment. | Shipping Integration | Speaker 3 | 05-01 Meeting: Shipping Integration Enhancements & Standardization | Medium | Open | 2026-05-18
089 | will respond to Sabir's query, confirming that markup percentages should be... | [Speaker 3] will respond to Sabir's query, confirming that markup percentages should be maintained at the carrier service level. | Shipping Integration | Speaker 3 | 05-01 Meeting: Shipping Integration Enhancements & Standardization | Medium | Open | 2026-05-18
090 | Check with developer if WWX service codes added in D365 will auto-map to... | Check with developer if WWX service codes added in D365 will auto-map to shipping integration; define code changes if needed. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
091 | Ensure WWX carrier service names (e.g., SIA, Old Dominion, R+L, FedEx... | Ensure WWX carrier service names (e.g., SIA, Old Dominion, R+L, FedEx Freight) display in the shipping window. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
092 | Confirm which UPS API fields provide discounted vs. published rates and... | Confirm which UPS API fields provide discounted vs. published rates and update the FDD accordingly. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
093 | Add fields/mapping to store UPS discounted rate alongside published rate in... | Add fields/mapping to store UPS discounted rate alongside published rate in the integration result (shipment) context. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
094 | Decide whether integration result table alone suffices or if maintain... | Decide whether integration result table alone suffices or if maintain charges table also needs the new fields; align with Paul/Matthew. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
095 | Implement default 20% markup for UPS at carrier level, with ability to... | Implement default 20% markup for UPS at carrier level, with ability to override by service (e.g., Next Day Air 10%, Ground 25%). | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
096 | Update the AEO request to reflect scope changes (adding discounted rate... | Update the AEO request to reflect scope changes (adding discounted rate storage; carrier/service-level markup logic). | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
097 | Establish testing steps and sample cases (e.g., Next Day Air example: $150... | Establish testing steps and sample cases (e.g., Next Day Air example: $150 published vs. ~$40 discounted) to verify mapping and calculations end-to-end. | Shipping Integration | TBD | 05-01 Meeting: D365 Shipping Integration - UPS/WWX Markup, Service Mapping, and Rate Handling | Medium | Open | 2026-05-18
098 | Confirm with Seth Beer that both discounted and published rates can be... | [Speaker 4] Confirm with Seth Beer that both discounted and published rates can be retrieved via the UPS API. | Freight Policy | Speaker 4 | 05-01 Weekly Meeting: Freight Charge Reporting and Markup Management | Medium | Open | 2026-05-18
099 | Verify with WWX and Global Trends whether a published rate can be provided;... | [Speaker 4] Verify with WWX and Global Trends whether a published rate can be provided; current understanding is only the discounted rate is available. | Freight Policy | Speaker 4 | 05-01 Weekly Meeting: Freight Charge Reporting and Markup Management | Medium | Open | 2026-05-18
100 | Provide the complete markup percentage breakdown for all delivery modes... | [Speaker 4] Provide the complete markup percentage breakdown for all delivery modes (UPS, LTL, hot shots) in the ADO ticket. | Freight Policy | Speaker 4 | 05-01 Weekly Meeting: Freight Charge Reporting and Markup Management | Medium | Open | 2026-05-18
101 | Send a follow-up email summarizing the discussion and confirming next steps. | [Speaker 4] Send a follow-up email summarizing the discussion and confirming next steps. | Freight Policy | Speaker 4 | 05-01 Weekly Meeting: Freight Charge Reporting and Markup Management | Medium | Open | 2026-05-18
102 | Document his understanding of the requirements and share with [Speaker 4]... | [Speaker 2] Document his understanding of the requirements and share with [Speaker 4] after his next meeting. | Freight Policy | Speaker 2 | 05-01 Weekly Meeting: Freight Charge Reporting and Markup Management | Medium | Open | 2026-05-18
103 | will configure two auto-print jobs for Baton Rouge to run at 8:00 AM and... | [Speaker 3] will configure two auto-print jobs for Baton Rouge to run at 8:00 AM and 1:00 PM. | Freight Operations | Speaker 3 | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
104 | The new auto-print process will begin at 1:00 PM on May 1, 2026, for testing. | The new auto-print process will begin at 1:00 PM on May 1, 2026, for testing. | Freight Operations | TBD | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
105 | will set up a test email notification job for Baton Rouge. | [Speaker 3] will set up a test email notification job for Baton Rouge. | Freight Operations | Speaker 3 | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
106 | will send the list of all available printers to [Speaker 2]. | [Speaker 3] will send the list of all available printers to [Speaker 2]. | Freight Operations | Speaker 3 | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
107 | will identify the correct printer for each location and provide the... | [Speaker 2] will identify the correct printer for each location and provide the information to [Speaker 3]. | Freight Operations | Speaker 2 | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
108 | will schedule a follow-up meeting for the week of May 11, 2026, to review... | [Speaker 2] will schedule a follow-up meeting for the week of May 11, 2026, to review feedback and discuss broader rollout. | Freight Operations | Speaker 2 | 05-01 Meeting: Automated Shipping Pick List Printing Configuration | Medium | Open | 2026-05-18
109 | Send photos of Mason Ewing items to Lane for interest/decision. | Send photos of Mason Ewing items to Lane for interest/decision. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
110 | Complete the inventory evaluation sheet and share access with Alan by... | Complete the inventory evaluation sheet and share access with Alan by 2026-05-01; ensure item number clarifications in 365 are finalized. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
111 | Run usage reports on the finalized item list to guide keep/dispose decisions. | Run usage reports on the finalized item list to guide keep/dispose decisions. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
112 | Verify the Baton Rouge Orbit PO line by line; reconcile physical inventory... | Verify the Baton Rouge Orbit PO line by line; reconcile physical inventory vs. Oracle records by 2026-05-03. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
113 | Decide and document handling for previously written-off/on Orbit items after... | Decide and document handling for previously written-off/on Orbit items after verification, including accounting entries and site ownership. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
114 | Schedule metal dumpster pickup and order a roll-off construction dumpster by... | Schedule metal dumpster pickup and order a roll-off construction dumpster by 2026-05-02. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
115 | Conduct a quick floor walkthrough to mark items for dumpster vs.... | Conduct a quick floor walkthrough to mark items for dumpster vs. retention/transfer by 2026-05-02; review painted/partial bodies without bonnets for scrap. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
116 | Plan and install additional rack beams to utilize vertical space; define and... | Plan and install additional rack beams to utilize vertical space; define and label standardized locations without blocking crane access or front area operations. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
117 | Arrange optional support (e.g., Anthony) for coordination and forklift... | Arrange optional support (e.g., Anthony) for coordination and forklift operations during cleanup. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
118 | Remove the trailer to free space and confirm the parking layout. | Remove the trailer to free space and confirm the parking layout. | Inventory Management | TBD | 04-29 Operations Meeting: Inventory Reconciliation, Orbit Valve Ownership, and Racking Optimization | Medium | Open | 2026-05-18
119 | Validate whether WEx scenario calculations include all relevant accessorials... | Validate whether WEx scenario calculations include all relevant accessorials and surcharges; define included components explicitly. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
120 | Share the updated WEx analysis file with final formula references and column... | Share the updated WEx analysis file with final formula references and column definitions. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
121 | Run sensitivity analysis for alternate discount levels (e.g., 55%, 70%)... | Run sensitivity analysis for alternate discount levels (e.g., 55%, 70%) across the full 12-month dataset. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
122 | Define the organization's freight pricing goal/guardrails (e.g., target... | Define the organization's freight pricing goal/guardrails (e.g., target margin, net recovery) and document decision criteria and approval path. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
123 | Model and validate each division's one-pager within the shared pricing model... | Model and validate each division's one-pager within the shared pricing model before finalizing. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
124 | Establish and document policy for intercompany transfers (no markup rules,... | Establish and document policy for intercompany transfers (no markup rules, cost allocation, and customer charge timing). | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
125 | Provide additional shipping data to re-shop LTL tariffs; ensure mechanisms... | Provide additional shipping data to re-shop LTL tariffs; ensure mechanisms retain rate improvements in margin. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
126 | Roll out transportation policy to Sales; equip teams with talk tracks and an... | Roll out transportation policy to Sales; equip teams with talk tracks and an escalation path for pushback; continue "top offenders" conversion. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
127 | Complete parcel configuration and automation tickets (published +10% and... | Complete parcel configuration and automation tickets (published +10% and "publish x10%" calc); assign ownership and target dates; confirm deployment. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
128 | Maintain bundled "freight and handling" invoice line unless business... | Maintain bundled "freight and handling" invoice line unless business decision dictates breakout; evaluate the breakout ticket. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
129 | Update written rules to state applicability to inbound and outbound... | Update written rules to state applicability to inbound and outbound shipments and ensure consistency across modes. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
130 | Confirm with Tom the methodology/data supporting the $0.43/lb inbound LTL... | Confirm with Tom the methodology/data supporting the $0.43/lb inbound LTL rate; document update cadence and ownership. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
131 | Define and document exception thresholds and processes for... | Define and document exception thresholds and processes for oversize/overlength shipments and associated charges. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
132 | Finalize one-pager freight/fees policy after edits and approvals; [Speaker... | Finalize one-pager freight/fees policy after edits and approvals; [Speaker 3] to brief directors/managers; enforce standardized practices. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
133 | Clarify and document tariff handling matrix: 30% markup on supplier-invoiced... | Clarify and document tariff handling matrix: 30% markup on supplier-invoiced tariffs; pass-through rules for importer-of-record customs per David's authorization. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
134 | Confirm and publish company-owned truck fee at $2.50/mile with exception... | Confirm and publish company-owned truck fee at $2.50/mile with exception rules and multi-stop handling. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
135 | Resolve dropship policy details (markup vs. recovery model) with Pam and... | Resolve dropship policy details (markup vs. recovery model) with Pam and inside sales; deliver final to Justin. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
136 | Create and process a ticket to add the "exception" delivery term; ensure... | Create and process a ticket to add the "exception" delivery term; ensure reporting capability. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
137 | Share the updated master policy document and latest workbook with all... | Share the updated master policy document and latest workbook with all participants; confirm access. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
138 | Validate UPS small parcel markup (published + 40% vs. discounted + 60%) with... | Validate UPS small parcel markup (published + 40% vs. discounted + 60%) with real data; update policy accordingly. | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
139 | Define and communicate the approval path for exceptions (divisional VP Sales... | Define and communicate the approval path for exceptions (divisional VP Sales and Ops). | Freight Policy | TBD | 04-29 Meeting: Freight Pricing Strategy, WEx Analysis, and Policy Rollout | Medium | Open | 2026-05-18
140 | Provide confirmation on the completed Sprint 5 item (Thomas/Carolina). | Provide confirmation on the completed Sprint 5 item (Thomas/Carolina). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
141 | Restore email functionality for unit tests to enable email template testing... | Restore email functionality for unit tests to enable email template testing ([Speaker 3], [Speaker 1]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
142 | Validate customer contacts cleanup with updated datasets; provide update by... | Validate customer contacts cleanup with updated datasets; provide update by 2026-04-29 ([Speaker 4], Joel). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
143 | Discuss POs tied to production orders after the inventory picking call;... | Discuss POs tied to production orders after the inventory picking call; schedule a deeper session with Donna if needed ([Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
144 | Deliver the revised FDD for replacement/standard cost (Jimmy, [Speaker 1] to... | Deliver the revised FDD for replacement/standard cost (Jimmy, [Speaker 1] to [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
145 | Obtain the inventory "bill of authority" doc from Rocky and schedule the... | Obtain the inventory "bill of authority" doc from Rocky and schedule the workflow approvals session (Ellen, [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
146 | Open/escalate a Microsoft ticket for the Prod-to-Dev copy issue as needed;... | Open/escalate a Microsoft ticket for the Prod-to-Dev copy issue as needed; share status ([Speaker 1], [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
147 | Move procurement category restriction work to unit test when ready ([Speaker... | Move procurement category restriction work to unit test when ready ([Speaker 1]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
148 | Finalize the plan and schedule for full cycle count testing ([Alan],... | Finalize the plan and schedule for full cycle count testing ([Alan], [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
149 | Check in code for the assigned development item ([Speaker 4]). | Check in code for the assigned development item ([Speaker 4]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
150 | Determine sprint placement for the quoting bill of authority and schedule as... | Determine sprint placement for the quoting bill of authority and schedule as bandwidth allows ([Speaker 2], [Speaker 1], Jimmy, Paul, Thomas). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
151 | Respond to questions on wrong email destination and schedule a call with... | Respond to questions on wrong email destination and schedule a call with Greg and Hector ([Speaker 7], [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
152 | Complete testing and report results for the customer account statement email... | Complete testing and report results for the customer account statement email correction (tester to [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
153 | Complete and share the updated FDD/acceptance criteria for shipping... | Complete and share the updated FDD/acceptance criteria for shipping integration changes; [Speaker 2] to review ([Speaker 8], [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
154 | Clarify if DHL is in scope for connectivity; schedule a FedEx/DHL alignment... | Clarify if DHL is in scope for connectivity; schedule a FedEx/DHL alignment meeting (Alan, Paul, [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
155 | Comment and have Charlie re-submit cycle counting plans to unit test... | Comment and have Charlie re-submit cycle counting plans to unit test ([Speaker 2], [Speaker 7]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
156 | Load new tier pricing data with priority over security settings ([Speaker 5]). | Load new tier pricing data with priority over security settings ([Speaker 5]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
157 | Review custom alerts batch job details and advise Alfredo on next steps... | Review custom alerts batch job details and advise Alfredo on next steps ([Speaker 2], Alfredo). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
158 | Complete security restrictions after Carl's upload; target by 2026-04-29... | Complete security restrictions after Carl's upload; target by 2026-04-29 ([Speaker 4]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
159 | Schedule a call with Ryan (and possibly Scott) to resolve the "suggest to... | Schedule a call with Ryan (and possibly Scott) to resolve the "suggest to apply" 24-item stop ([Speaker 10]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
160 | Schedule an early-morning session with Paul and Joel to define the... | Schedule an early-morning session with Paul and Joel to define the auto-print pick list batch schedule for Setpoint and WNO Europe ([Alan]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
161 | Add access details for Ben Landrew and align timing within the security role... | Add access details for Ben Landrew and align timing within the security role project (Mohamed, [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
162 | Proceed with the Canopy/Alfredo fix for the intercompany packing slip PO... | Proceed with the Canopy/Alfredo fix for the intercompany packing slip PO number; update the managed services thread ([Speaker 1], Alfredo). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
163 | Decide who performs the CE refresh (Canby vs. internal), confirm CE... | Decide who performs the CE refresh (Canby vs. internal), confirm CE environments (A/B) and dual-write links, and execute the refresh ([Speaker 7], Paul, [Speaker 1], [Speaker 2]). | ERP/D365 | TBD | 04-28 Stand-up Meeting: Sprint 5/6 Blockers, Email Testing, CE Refresh, Shipping & Carrier Scope | Medium | Open | 2026-05-18
164 | Adam: Discuss the budget and unit choice with his wife. | Adam: Discuss the budget and unit choice with his wife. | General | TBD | 04-28 Consultation: Adam - Commercial Space | Medium | Open | 2026-05-18
165 | Adam: Run financial calculations to confirm affordability of the $1200/month... | Adam: Run financial calculations to confirm affordability of the $1200/month unit. | General | TBD | 04-28 Consultation: Adam - Commercial Space | Medium | Open | 2026-05-18
166 | Adam: Text the owner his name to save contact information. | Adam: Text the owner his name to save contact information. | General | TBD | 04-28 Consultation: Adam - Commercial Space | Medium | Open | 2026-05-18
167 | Adam: Provide a final decision by the end of the week (by May 2, 2026). | Adam: Provide a final decision by the end of the week (by May 2, 2026). | General | TBD | 04-28 Consultation: Adam - Commercial Space | Medium | Open | 2026-05-18
168 | Owner: Follow up with Adam if no response by the end of the week. | Owner: Follow up with Adam if no response by the end of the week. | General | TBD | 04-28 Consultation: Adam - Commercial Space | Medium | Open | 2026-05-18
169 | Define specific steps to improve traction on cycle counts, including owner... | Define specific steps to improve traction on cycle counts, including owner assignment and timelines. | Inventory Management | TBD | 04-28 Meeting: Cycle Count Improvements and Freight Ticket Resolution | Medium | Open | 2026-05-18
170 | Identify requirements and resources needed to progress on freight-related... | Identify requirements and resources needed to progress on freight-related tickets, including owner assignment and timelines. | Inventory Management | TBD | 04-28 Meeting: Cycle Count Improvements and Freight Ticket Resolution | Medium | Open | 2026-05-18
171 | Finalize and publish the company-wide freight policy. | Finalize and publish the company-wide freight policy. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
172 | Carl to complete the review of the top W&O prepaid customers by April 29, 2026. | Carl to complete the review of the top W&O prepaid customers by April 29, 2026. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
173 | to visit Stafford to confirm the use of "publish rate" before the SunSource... | [Alan] to visit Stafford to confirm the use of "publish rate" before the SunSource call on April 29, 2026. | Freight Policy | Alan | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
174 | Speaker 2 to integrate the documents from Don, Rocky, and Hector into the... | Speaker 2 to integrate the documents from Don, Rocky, and Hector into the main policy document for the SunSource call. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
175 | Rocky to make a final edit to his document and resubmit it. | Rocky to make a final edit to his document and resubmit it. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
176 | Implement system changes for the new invoicing policy, exemption approval... | Implement system changes for the new invoicing policy, exemption approval process, and freight line items. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
177 | Bring up the proposal to create a freight "exempt" code for broader... | Bring up the proposal to create a freight "exempt" code for broader discussion and approval. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
178 | Speaker 2 to get clarification on Hector's team's process for UPS small... | Speaker 2 to get clarification on Hector's team's process for UPS small parcel markups. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
179 | Investigate why customer delivery and set point deliveries are not being... | Investigate why customer delivery and set point deliveries are not being charged freight. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
180 | Confirm if the existing freight part numbers can be used with a percentage... | Confirm if the existing freight part numbers can be used with a percentage for BOMs and kits. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
181 | Determine who is responsible for the current 3% freight markup and how it is... | Determine who is responsible for the current 3% freight markup and how it is technically applied. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
182 | Get input from Tom and Steve on standardizing the inbound freight capture... | Get input from Tom and Steve on standardizing the inbound freight capture process. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
183 | Complete analysis on WWE XL LTL outbound costs to evaluate a possible markup... | Complete analysis on WWE XL LTL outbound costs to evaluate a possible markup increase. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
184 | Attend the new recurring weekly meeting on Mondays at 3:30 PM and the... | Attend the new recurring weekly meeting on Mondays at 3:30 PM and the SunSource call on Wednesday, April 29, 2026. | Freight Policy | TBD | 04-27 Weekly Meeting: Freight Policy and System Implementation | Medium | Open | 2026-05-18
185 | Define and implement desired behavior for changing delivery terms: restrict... | Define and implement desired behavior for changing delivery terms: restrict changes in the integration form or ensure changes update the shipment header; document cancel/recreate workflow before packing. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
186 | Analyze frequency of delivery term changes and evaluate reducing the number... | Analyze frequency of delivery term changes and evaluate reducing the number of delivery term options; propose a simplified set. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
187 | Create a new ticket for default markup logic and related security... | Create a new ticket for default markup logic and related security restrictions; design security roles/privileges for viewing/editing markup. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
188 | Verify primary keys and constraints of the charge configuration table to... | Verify primary keys and constraints of the charge configuration table to support service-level and location-level defaults; confirm integration lookup logic for service/site/warehouse. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
189 | Assess feasibility and effort to maintain service lists for WEX in D365 to... | Assess feasibility and effort to maintain service lists for WEX in D365 to support service-level markup rules. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
190 | Review out-of-the-box D365 Transportation module capabilities vs custom... | Review out-of-the-box D365 Transportation module capabilities vs custom approach for future carriers; define analysis plan. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
191 | Align FedEx API request build with existing process flow and finalize... | Align FedEx API request build with existing process flow and finalize technical mapping. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
192 | Assess feasibility of storing carrier account numbers at delivery address... | Assess feasibility of storing carrier account numbers at delivery address level; ensure shipping integration defaults account numbers from customer-level fields. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
193 | Validate that maintain charges and order tracking views contain all required... | Validate that maintain charges and order tracking views contain all required fields for audit/reporting. | Shipping Integration | TBD | 04-27 Project Meeting: D365 Freight Recapture, Shipping Integration Enforcement, and Rate Standardization | Medium | Open | 2026-05-18
194 | Define policy to default new customers to "Prepay and Add," with an... | Define policy to default new customers to "Prepay and Add," with an exception flag for agreed no-freight accounts. | Freight Policy | TBD | 04-27 Meeting: Freight Leakage and Customer Policy Review | Medium | Open | 2026-05-18
195 | Assess feasibility of storing multiple carrier account numbers per... | Assess feasibility of storing multiple carrier account numbers per customer/location; evaluate required customization and auto-population into shipping integration; ensure warehouse override capability. | Freight Policy | TBD | 04-27 Meeting: Freight Leakage and Customer Policy Review | Medium | Open | 2026-05-18
196 | Schedule and conduct the 11:30 meeting with Sabir; include [Speaker 3];... | Schedule and conduct the 11:30 meeting with Sabir; include [Speaker 3]; confirm time zone and agenda. | Freight Policy | TBD | 04-27 Meeting: Freight Leakage and Customer Policy Review | Medium | Open | 2026-05-18
197 | will schedule a 30-minute follow-up call today at 2:00 PM to continue the... | [Alan] will schedule a 30-minute follow-up call today at 2:00 PM to continue the discussion. | ERP/D365 | Alan | 04-17 Meeting: Receiving Process and Dynamics 365 System Improvement | Medium | Open | 2026-05-18
198 | will investigate why the sales/production order reference number is not... | [Alan] will investigate why the sales/production order reference number is not visible in the item arrival journal in Dynamics 365 and report back. | ERP/D365 | Alan | 04-17 Meeting: Receiving Process and Dynamics 365 System Improvement | Medium | Open | 2026-05-18
199 | Schedule a call with Justin to align on expectations and approach for the... | Schedule a call with Justin to align on expectations and approach for the 30-day executive briefing. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
200 | Review the sample executive summary spreadsheet sent by Nathan to understand... | Review the sample executive summary spreadsheet sent by Nathan to understand a high-level reporting format. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
201 | Begin structuring the 30-day executive briefing by identifying approximately... | Begin structuring the 30-day executive briefing by identifying approximately five key areas that will benefit the business. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
202 | Practice the productivity technique of isolating himself to allow for... | Practice the productivity technique of isolating himself to allow for focused, strategic work. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
203 | Feel free to ping Nathan with any questions about the IDP as they arise. | Feel free to ping Nathan with any questions about the IDP as they arise. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
204 | Send Alan the spreadsheet example of an executive summary. | Send Alan the spreadsheet example of an executive summary. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
205 | Keep Alan's objectives in mind and share any helpful examples or thoughts... | Keep Alan's objectives in mind and share any helpful examples or thoughts over the next few weeks. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
206 | Schedule a follow-up meeting with Alan in May to discuss the other... | Schedule a follow-up meeting with Alan in May to discuss the other objectives in his development plan. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
207 | During future sessions, walk Alan through pro forma financial calculations... | During future sessions, walk Alan through pro forma financial calculations to help him understand the bottom-line impact of his operational decisions. | General | TBD | 04-17 Mentorship Session on Warehouse Leadership Development and Integration Strategy | Medium | Open | 2026-05-18
208 | Confirm UPS rate basis (published vs. discounted) with UPS account manager... | Confirm UPS rate basis (published vs. discounted) with UPS account manager and communicate to SunSource. | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
209 | Decide and publish divisional UPS markup defaults (target 20-25%; minimum... | Decide and publish divisional UPS markup defaults (target 20-25%; minimum 10% for immediate use). | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
210 | Provide divisional percentages to push into system once controls are ready... | Provide divisional percentages to push into system once controls are ready (UPS 10% or 20%, WWX 25%). | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
211 | Implement default markup in shipping integration via SR; restrict edit... | Implement default markup in shipping integration via SR; restrict edit rights to supervisors/managers+. | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
212 | Issue interim guidance for hot shot markup and ensure consistent manual... | Issue interim guidance for hot shot markup and ensure consistent manual entry across branches. | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
213 | Compile and share freight-related SR ticket list; prioritize against sprint... | Compile and share freight-related SR ticket list; prioritize against sprint schedules considering the 6-week constraint. | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
214 | Prioritize cycle-count-related tickets and evaluate potential inclusion in... | Prioritize cycle-count-related tickets and evaluate potential inclusion in sprint six. | Freight Policy | TBD | 04-17 Meeting: UPS Rate Basis, Freight Markup, and System Automation Strategy | Medium | Open | 2026-05-18
215 | Inactivate "Prepay" in Dynamics 365 and define the replacement term for... | Inactivate "Prepay" in Dynamics 365 and define the replacement term for existing records. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
216 | Export customer data; filter all with "Prepay"; update to "Prepaid & Add" or... | Export customer data; filter all with "Prepay"; update to "Prepaid & Add" or the appropriate term; re-import. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
217 | Engage Paul and Amy to coordinate the export/update/import process and... | Engage Paul and Amy to coordinate the export/update/import process and governance. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
218 | Commercial team to review and confirm which customers require "Collect." | Commercial team to review and confirm which customers require "Collect." | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
219 | Add a required field in SmartSheet for Collect account numbers on new... | Add a required field in SmartSheet for Collect account numbers on new customer setups. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
220 | Consultants to propose and configure a repurposed field for the Collect... | Consultants to propose and configure a repurposed field for the Collect account number in Customer Master; integrate to auto-populate on sales orders and shipments. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
221 | Align and publish standard defaults: FOB = Origin; default ship via;... | Align and publish standard defaults: FOB = Origin; default ship via; validation rules for carrier account numbers. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
222 | Communicate process changes to Customer Service and Warehouse teams. | Communicate process changes to Customer Service and Warehouse teams. | ERP/D365 | TBD | 04-16 Meeting: ERP Customer Setup Ownership, Delivery Terms Standardization, and AR Process Cleanup | Medium | Open | 2026-05-18
223 | Travel to Pasadena to assist with the inventory process. | Travel to Pasadena to assist with the inventory process. -- Alan | Inventory Management | Alan | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
224 | Implement a standardized labeling system for all items during the cleanup... | Implement a standardized labeling system for all items during the cleanup process. -- Jay | Inventory Management | Jay | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
225 | Create a laminated guide that standardizes measurements for bar stock, pipe,... | Create a laminated guide that standardizes measurements for bar stock, pipe, and other materials measured by feet or inches, and place it near the storage area. | Inventory Management | TBD | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
226 | Validate inventory data by exporting it and analyzing it for SMOI... | Validate inventory data by exporting it and analyzing it for SMOI (Slow-Moving and Obsolete Inventory) and overall movement. Items with no movement in Oracle for a defined period will be classified as SMOI. | Inventory Management | TBD | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
227 | Create a sheet listing all items in the yard to begin assessing what to keep... | Create a sheet listing all items in the yard to begin assessing what to keep and what to dispose of. -- Jay | Inventory Management | Jay | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
228 | Recount inventory in the yard once the cleanup is complete. | Recount inventory in the yard once the cleanup is complete. -- Jay's managers | Inventory Management | Jay's managers | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
229 | Recount the W&O valve source inventory when it is moved to the new building. | Recount the W&O valve source inventory when it is moved to the new building. -- Jay's managers | Inventory Management | Jay's managers | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
230 | Coordinate the timing of relocating people, tools, and benches to minimize... | Coordinate the timing of relocating people, tools, and benches to minimize production disruption, considering the pressure to support SRS orders. -- Jay | Inventory Management | Jay | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
231 | Move the W&O valve source inventory to the new building. Target: May. | Move the W&O valve source inventory to the new building. Target: May. | Inventory Management | TBD | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
232 | Process contractor payment so racking can be installed in the new building. | Process contractor payment so racking can be installed in the new building. | Inventory Management | TBD | 04-16 Meeting: Inventory Cleanup, Standardization, and Relocation | Medium | Open | 2026-05-18
233 | Determine if it's necessary to distinguish between records from the "disable... | [Alan] Determine if it's necessary to distinguish between records from the "disable integration" function and those manually added in "maintain charges." | Shipping Integration | Alan | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
234 | Confirm whether the freight markup percentage should be set at the header... | [Alan] Confirm whether the freight markup percentage should be set at the header (e.g., WWX) or carrier/service level. | Shipping Integration | Alan | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
235 | Investigate the technical feasibility of setting markup percentages at the... | [Speaker 1] Investigate the technical feasibility of setting markup percentages at the carrier/service level for WWX. | Shipping Integration | Speaker 1 | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
236 | Begin drafting the FDD for the confirmed items: privileges on the rate shop... | [Speaker 1] Begin drafting the FDD for the confirmed items: privileges on the rate shop window and adding custom fields for original rate and shipping carrier. | Shipping Integration | Speaker 1 | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
237 | Add a comment to the task noting that the FDD for the first two items is in... | [Speaker 1] Add a comment to the task noting that the FDD for the first two items is in progress. | Shipping Integration | Speaker 1 | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
238 | Create a new ticket to store and default the customer's collect account number. | [Alan] Create a new ticket to store and default the customer's collect account number. | Shipping Integration | Alan | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
239 | Review the FedEx FDD. | [Alan] Review the FedEx FDD. | Shipping Integration | Alan | 04-16 Weekly Meeting: Shipping Integration and Rate Customization | Medium | Open | 2026-05-18
240 | Speaker 1 and Steve will review the draft freight policy document. | Speaker 1 and Steve will review the draft freight policy document. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
241 | Speaker 1 will share the policy with Jim for his review and feedback. | Speaker 1 will share the policy with Jim for his review and feedback. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
242 | Alan (Alan) will meet with divisional leaders (Don, Hector, Rocky) to scrub... | Alan (Alan) will meet with divisional leaders (Don, Hector, Rocky) to scrub the list of D365 delivery terms and push for standardization. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
243 | Schedule a follow-up call with Tom, Amy, and Paul to discuss the data... | Schedule a follow-up call with Tom, Amy, and Paul to discuss the data migration from the old system. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
244 | Have a conversation with customer service leadership about the use of the... | Have a conversation with customer service leadership about the use of the "prepaid" freight code. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
245 | Investigate how to configure default delivery terms, shipping methods, and... | Investigate how to configure default delivery terms, shipping methods, and collect account numbers at the customer account and ship-to address levels in D365. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
246 | Determine the effort required for customer service/sales to validate and... | Determine the effort required for customer service/sales to validate and populate the missing account-level shipping data. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
247 | The team aims to finalize the policy and communication plan by the end of... | The team aims to finalize the policy and communication plan by the end of next week. | Freight Policy | TBD | 04-15 Meeting: Enterprise Freight Policy Development and ERP Integration | Medium | Open | 2026-05-18
248 | Compile and finalize ABC classifications for all items; share with the team.... | Compile and finalize ABC classifications for all items; share with the team. Deadline: today if possible. Stakeholder: Alan, Amy. | Inventory Management | Alan, Amy | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
249 | Import finalized ABC classifications into D365 using the data entity... | Import finalized ABC classifications into D365 using the data entity provided. Stakeholder: Mudassir (with support from Sabir). | Inventory Management | Mudassir (with support from Sabir) | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
250 | Set up stakeholder meeting (Amy, Paul, John, Sabir, Alan) to decide between... | Set up stakeholder meeting (Amy, Paul, John, Sabir, Alan) to decide between item-level (ABC) vs. location-based approach. Target: Thursday or Friday. | Inventory Management | TBD | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
251 | Define cycle counting frequencies per class (e.g., A twice/year, B... | Define cycle counting frequencies per class (e.g., A twice/year, B once/year, C annually/half-time) and align days-between settings. Stakeholders: Warehouse managers, Amy, Paul. | Inventory Management | Warehouse managers, Amy, Paul | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
252 | Develop SOP for new item onboarding, mandating ABC assignment (default C)... | Develop SOP for new item onboarding, mandating ABC assignment (default C) and/or inclusion in a separate plan until classified. Stakeholders: Product master data team. | Inventory Management | Product master data team | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
253 | Configure D365 cycle counting plans: product queries for item-level ABC,... | Configure D365 cycle counting plans: product queries for item-level ABC, appropriate maximum counts (e.g., 50/day), and scheduling. Stakeholder: Sabir. | Inventory Management | Sabir | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
254 | Conduct unit tests in UAT to validate item-level vs. location-level... | Conduct unit tests in UAT to validate item-level vs. location-level behaviors, mobile device prompts, and workload balance. Stakeholders: Sabir, warehouse workers. | Inventory Management | Sabir, warehouse workers | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
255 | Gather pilot feedback from Houston and plan a comparative pilot in... | Gather pilot feedback from Houston and plan a comparative pilot in Cincinnati, adjusting counts based on worker capacity. Stakeholders: Warehouse managers. | Inventory Management | Warehouse managers | 04-15 Workshop: D365 Cycle Counting Strategy and ABC Configuration for Houston & Cincinnati Warehouses | Medium | Open | 2026-05-18
256 | Analyze tracking number formats (e.g., UPS "1Z", WWE patterns) and propose... | [Speaker 1] (Sabir): Analyze tracking number formats (e.g., UPS "1Z", WWE patterns) and propose Description-based conditions to identify integration charges. | Freight Operations | Speaker 1 | 04-14 Project Meeting: Power BI Freight Reporting - Carrier Costs vs Customer Charges, Integration vs Manual, Inbound vs Outbound | Medium | Open | 2026-05-18
257 | Validate cases where the "Outbound freight" Description appears and confirm... | [Speaker 1] (Sabir): Validate cases where the "Outbound freight" Description appears and confirm exclusion logic for the integration bucket. | Freight Operations | Speaker 1 | 04-14 Project Meeting: Power BI Freight Reporting - Carrier Costs vs Customer Charges, Integration vs Manual, Inbound vs Outbound | Medium | Open | 2026-05-18
258 | Add new columns in Power BI - Freight Cost (integration outbound), Manual... | [Speaker 3] (Matt): Add new columns in Power BI - Freight Cost (integration outbound), Manual Freight Charges, and Total Cost; ensure Freight Revenue includes both header and line charges. | Freight Operations | Speaker 3 | 04-14 Project Meeting: Power BI Freight Reporting - Carrier Costs vs Customer Charges, Integration vs Manual, Inbound vs Outbound | Medium | Open | 2026-05-18
259 | Assess the feasibility of joining to the packing slip journal's custom table... | [Speaker 3] (Matt): Assess the feasibility of joining to the packing slip journal's custom table for more accurate integration flags if Description logic proves insufficient. | Freight Operations | Speaker 3 | 04-14 Project Meeting: Power BI Freight Reporting - Carrier Costs vs Customer Charges, Integration vs Manual, Inbound vs Outbound | Medium | Open | 2026-05-18
260 | Create and share a follow-up item summarizing required report changes and... | [Speaker 2] (Alan): Create and share a follow-up item summarizing required report changes and timelines. | Freight Operations | Speaker 2 | 04-14 Project Meeting: Power BI Freight Reporting - Carrier Costs vs Customer Charges, Integration vs Manual, Inbound vs Outbound | Medium | Open | 2026-05-18
007 | Schedule and hold cycle counts follow-up session | Alan to send a calendar invite for a separate session focused on cycle counts. Agreed at the end of the April 14 meeting as a distinct follow-up. | Cycle Counts | Alan | 2026-04-14 | Low | Complete | 2026-04-14

## Summary
Action Tracker — Summary
Total items: 260
Status | Count | Priority | Count | Category | Count
Open | 254 | High | 3 | Freight Policy | 68
In Progress | 0 | Medium | 256 | ERP/D365 | 52
Blocked | 0 | Low | 1 | Shipping Integration | 45
Complete | 6 |  |  | Freight Operations | 37
Not Applicable | 0 |  |  | Inventory Management | 37
|  |  |  | General | 14
|  |  |  | Delivery Terms | 2
|  |  |  | Freight Revenue | 1
|  |  |  | Security & Access | 1
|  |  |  | Development Review | 1
|  |  |  | Ticketing & Support | 1
|  |  |  | Cycle Counts | 1